## Sheet1
Tasks |  | Who`s handling |  | Status | Priority
| Scrum Master | Product Owner | Developers | Comments | 1-5
Code Board class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 1
Code Game class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 1 | מקרא צבעים
Code Difficulty class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1
Code Tile class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1 |  | הושלם ועבר אינטגרציה
Code Player class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 1 |  | בטיפול
Code Question class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1 |  | לא באיטרציה הנוכחית
Code Parser class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 1
Code Consts class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 1
Code SysData class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 1
Test Board class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 2
Test Game class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 2
Test Question class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 2
Code Parser class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 2
Code SysData class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 2
Code Board View Controller | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 1
Code Game View Controller | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 1
Code Questions View Controller | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 1
Code Rules View Controller | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija
Code TimeForPlayer Class | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 1
Build Borad View | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 1
Build New Game View | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 1
Build Questions View | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 1
Build Rules View | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 1
Prepare SE questions | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Test Board View Controller | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 2
Test Game View Controller | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 2
Test Questions View Controller | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Test Roles View Controller | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Test Views | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Tile Colors and colors functions | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 2
queen moves and skips | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 2
SOUND package | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Admin page | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
White box | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Black Box (Junit Package) | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Timer and Score | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Build history View | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Build load view | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Build play view | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 1
Build nickName view | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Build add question view | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Build update question view | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Build winner view | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Build popQuestion view | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code history view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Code loadGame view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Code play view Controller | Ayah Abu El-Hija | Rawi Jaraisry | All |  | 1
Code nickName view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code add question view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code update question view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code winner view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code popQuestion view Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Code piece class | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 1
Red tile | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 1
Blue tile | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan |  | 1
Tile factory | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Skips for queen | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Double eat | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 1
PlayeGame -Controller | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan & Rawi Jaraisry |  | 1
PopQ - Controller | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Board-Controller | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan & Rawi Jaraisry |  | 1
Color Tile Handler class | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 1
Data class | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 1
Timer for player | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Timer For the Game | Ayah Abu El-Hija | Rawi Jaraisry | Ayah Abu El-Hija |  | 1
Test Board | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan & Rawi Jaraisry |  | 2
Test Board View Controller | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan & Rawi Jaraisry |  | 2
Test red and blue tiles | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan |  | 2
Test history view controller | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 2
Test play controller | Ayah Abu El-Hija | Rawi Jaraisry | Rawi Jaraisry |  | 2
Test pop question | Ayah Abu El-Hija | Rawi Jaraisry | Amneh Hassan |  | 2
Test skips for queen | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 2
Test load game | Ayah Abu El-Hija | Rawi Jaraisry | Najwan Kanj |  | 2