## Sheet1
Tasks |  | Who`s handling |  | Status | Priority
| Scrum Master | Product Owner | Developers | Comments | 1-5
Code Board class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 1
Code Game class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 1 | מקרא צבעים
Code Difficulty class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1
Code Tile class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1 |  | הושלם ועבר אינטגרציה
Code Player class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 1 |  | בטיפול
Code Question class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 1 |  | לא באיטרציה הנוכחית
Code Parser class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 1
Code Consts class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 1
Code SysData class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 1
Test Board class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 2
Test Game class | Rawi Jaraisry | Najwan Kanj | Najwan Kanj |  | 2
Test Question class | Rawi Jaraisry | Najwan Kanj | Amneh Hassan |  | 2
Code Parser class | Rawi Jaraisry | Najwan Kanj | Rawi Jaraisy |  | 2
Code SysData class | Rawi Jaraisry | Najwan Kanj | Ayah Abu El-Hija |  | 2
Code Board View Controller | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 1
Code Game View Controller | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 1
Code Questions View Controller | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 1
Code Roles View Controller | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija
Code TimeForPlayer Class | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 1
Build Borad View | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 1
Build New Game View | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 1
Build Questions View | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 1
Build Roles View | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 1
Prepare SE questions | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Test Board View Controller | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 2
Test Game View Controller | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 2
Test Questions View Controller | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Test Roles View Controller | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Test Views | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Tile Ccolors and colors functions | Amneh Hassan | Ayah Abu El-Hija | Rawi Jaraisy |  | 2
queen moves and skips | Amneh Hassan | Ayah Abu El-Hija | Najwan Kanj |  | 2
SOUND package | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
Admin page | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2
White box | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Black Box (Junit Package) | Amneh Hassan | Ayah Abu El-Hija | Amneh Hassan |  | 2
Timer and Score | Amneh Hassan | Ayah Abu El-Hija | Ayah Abu El-Hija |  | 2